## Sheet1
|  | 0 - 20 |  |  | 21-30 |  | 31+
No. | Category | Description of risk | Owner | Other teams involved | Trigger | Probability (1: no prob, 10: certain) | Impact (1:no impact, 10: catastrophic) | Rating | Mitigation | Residual P/I risk | Review frequency | Action to be taken now | Already in place | Review Jun 2014 | Review Feb 2016 | Review Feb 2018 | Review Feb 2019 | Residual P/I risk
1 | Financial | Financial discrepancies as a result of internal and/or external action | Chair/Finance team | All | Unauthorised bank transactions, credit card fraud | 4 | 6 | 24 | Regular bank and CC statement reconciliations to flag issues early. (At least monthly). No further frauds detected to date | 12 | Review quarterly |  |  | Silajala does initial check. Achalavira checks again when reconciling. Both to initial statement | JH completes reconcilation weekly. Would be useful to have back up person trained to do this work. | Still need back up person trained to do this | 2 people being trained in use of Paxton | 12
[5 empty] | Petty cash discrepancies | 5 | 4 | 20 | Amount of petty cash reduced to max of £100. No. of times used very much reduced. | 9 | Review quarterly | PC procedure understood by team. Only team tohave access to PC tin. |  | Induction carried out for new and existing staff. See procedure below | No further action required beyond current process. | No further action required beyond current process. | No further action required | 9
[5 empty] | Discrepancies in shop cash box, loss of cash from dana bowl | 5 | 5 | 25 | Bookshop cash transferred to safe regularly. Dana bowl now has less in it as people use DD more, but still risk of money being taken out. | 20 | Review quarterly | Increase frequency of banking. Make sure cash tin is held securely out of public gaze. |  | Banking frequency deemed to be adequate. | Banking done weekly | Banking frequency deemed to be adequate. | Money transferred to safe every day, limiting the amount of cash in the dana bowl | 20
2 | Financial | Qualified audit report due to poor record keeping | Chair/finance team | None | Audit reveals discrepancies, incomplete records, inaccurate data | 3 | 7 | 21 | Maintain oversight of system use, through routine reconciliations. | 21 | at least 2x p.a. | Treasurer to work with team to ensure that at least 1 other person understands and can use Paxton |  | 2 members of team have access to Paxton - 1 stillundergoing training | This needs to be done by end of Summer - ? During August | 1 person now trained in some elements of Paxton. Further training required | 2 people being trained in using Paxton | 18
[5 empty] | Financial skills/training inadequate, leading to inaccurate recording of data | 4 | 8 | 32 | Ensure staff have training in system use | 24 | at least 2x p.a. | See above - in addition to personal training, use of internal manual and online training. |  | See above. New budget guidance being rolled out to team | Guidance written and at least 1 person trained | Still needs to be done. BY Summer 2018 | Guidance produced and 1 other person now can use the system | 21
3 | Operational | Loss or L/T absence of one or more key team members results in operational failure. | All |  | Unable to pay bills, produce reports, pay salaries, run classes etc, maintain buidling etc | 5 | 8 | 40 | Ensure all team members have written up key procedures and make available to rest of team. | 24 | quarterly | All team members to write up details of their activities by end of Summer |  |  | All team members to write up details of their activities by end of Summer | Still not done. Stand in staff to be identified and trained by Autumn 2018 | Still being reviewed | 24
4 | Operational | IT failure leading to loss of financial & other data | All | All | Chair alerted regularly via monthly reports. | 5 | 9 | 45 | Ensure use of up to date software, virus checking. Back up data off site. Use cloud technology. | 30 | quarterly | Formal record kept of when virus checker needs updating. All team to know and apply backup procedure. |  | Automatic checker established. | Awaiting Will to come and review systems and make recommendations for improving security and effectiveness | Appointed professional IT company to manage hardware and software including virus checking, data back up, cloud management. |  | 18
4 | Operational | Loss/reduction of one or more streams of funding | Chair | All | Standing Orders cancelled, room hire reduced, classes not fully subscribed | 5 | 8 | 40 | Early warning from finance team, will enable speedy response eg fundraising activities, letter to all friends etc. | 30 | Monthly | Chair alerted via monthly reports |  | Part of monthly finance report | No further action required beyond what is already in place | Active fundraising programme to be set up to make funds available for L/T plans |  | 25
| Operational | Inspection reveals failure to apply GDPR adequately | Chair |  | Personal information is found to be insecurely held | 4 | 8 | 32 | Ensure that all personal data is identified and held securely - method to be determined | 24 | quarterly | [5 empty] | New item in 2019
5 | Operational | Premises unusable due to (eg) fire, flood, explosion | Centre manager/Healing Rooms manager | All | Alarms activated, notification from police,staff members, public | 3 | 9 | 27 | All alarms fully functioning. Disaster recovery plan in place - alternative premises, IT back up, communication chain plan etc. | 21 | Quarterly | Team believes that current system would be adequate should this risk materialise. |  | No potentially disastrous events have taken place during the period. | Karunavapi to check schedules for alarm and PAT testing. Fire equipment checked and any recommendations implemented. | Admin kula to check schedules for alarm, fire equpt & PAT testing. Recommendations implemented. |  | 21
|  | Malicious behaviour resulting in significant damage to building/surroundings | Centre manager/Healing Rooms manager | All | Visible signs of damage or alert from (eg) police or public. | 5 | 7 | 35 | Consider current security measures - ?adequate. Potential problem with open access to back of building. | 30 | Quarterly | Consider current security measures - ?adequate |  |  | Consider current security measures - ?adequate. New building layout may reduce this risk further | Consider current security measures - ?adequate. New building layout may reduce this risk further |  | 30
|  | Lax security results in damage to premises and/or financial loss | Chair/centre manager |  | Incomplete record of key holders. Inappropriate assignment of keys | 5 | 7 | 35 | Identify all key holders. Do they all need keys? Get keys returned and securely locked away. | 28 | Quarterly | Review key holder list. |  |  | Likely that new building security (key pad) will reduce this problem further. | Likely that new building security (key pad) will reduce this problem further. |  | 28
6 | Health & Safety | Failure to comply with all relevant H & S legislation | Team |  | eg. Person injured by hatch door being inadequately secured, or tripping on stairs | 5 | 6 | 30 | Conduct H & S review. Implement all recommended changes | 24 | half yearly | Notice on hatch re: safe handling. Ensure team member present when using hatch. |  |  | Run training for staff to ensure increased awareness of risks | New H & S programme being updated |  | 24
7 | Reputational | Failure to comply with all appropriate legislation | Chair/Treasurer | All | Most likely issues could be HMRC, DWP, HSE, notifying failure to meet reporting/payment timetables. Others possibly equal opps, disability etc. | 4 | 7 | 28 | Sign up for alerts from HMRC, charity commission, charity groups. Ensure that all relevant changes are noted and acted on. | 18 | On going | Already signed up for hmrc, cc. ? Any others |  | Treasurer receives regular updates - shares key issues with trustees/finance | Existing action deemed adequate | Liaise with Central Triratna to ensure we're aware of what is being done elsewhere and introduce here |  | 18
| Reputational | Negative report from a Charity Commission review | Chair/Trustees |  | Trustees have not met their obligations re: oversight and management | 4 | 8 | 32 | Training for new trustees and updates for existing. Ensure all have CC guidelines on Trustees responsibilities | 24 | Half yearly | [5 empty] | New item in 2019
8 | Reputational | Negative publicity for centre and/or individuals connected with centre | Chair/Trustees | All | Negative comments on social media and elsewhere concerning ethical behaviour of centre 'members' | 3 | 6 | 18 | Open communication between order members, visitors, friends. Clear about adherence to ethical precepts. Prepared to take action to block -ve comments on social media -justifiable? | 18 | Monthly | Members to contribute to central response to any negative publicity. Review issues that could possibly give rise to negative comment. |  | No issues have arisen during the period under review | No issues have arisen during the period under review | No issues have arisen during the period under review |  | 18
9 | Reputational | Centre/member fails to act on duty of care issues where vulnerable people are concerned, resulting in potential harm to individual. | Chair/Trustees | All | Centre becomes aware of problems where person has mental/physical health issues of which they were not previously aware. | 3 | 8 | 24 | Decide on policy re: vulnerable people.Check all staff and rooms practitioners are aware of potential risk. | 18 | Annual | Decide on policy re: vulnerable people. Encourage increased awareness of potential issues. Set up emergency procedure in the event of potentially dangerous situation arising. |  | No action taken on this as yet. | Policy in progress | Policy in progress |  | 18
9 | Reputational | Failure to adhere to current safeguarding legislation concerning adults & children | Chair/Trustees | All |  | 3 | 8 | 24 |  | 18 | Annual | Decide on policy re: vulnerable people. Encourage increased awareness of potential issues. Set up emergency procedure in the event of potentially dangerous situation arising. |  | No action taken on this as yet. | Policy in progress | Policy in progress |  | 18